## Domain 3
CISA-DOMAIN 3
Information Systems Acquisition, Development & Implementation
Project management
Project management structure
1. functional structure >> project manager does not have formal authority ¦ work is divided in departments and manager can advise only
2. Project structure organization >> manager has authority over >> budget, schedule & team..
3. Matrix structure project organization >> authority is shared between manager and department heads.
Request for project initiation should be submitted to IT Steering Committee. Committee then identifies a project manager that doesn't need to be IT staff member.
Steering Committee >> Senior management + Project Sponsor + User Management + Project Manager
Roles & responsibilities
Project steering committee >>> overall direction + responsible for cost, budget and deliverables.
Senior management >> Commitment + approves resources
Project sponsor >> funds + assumes ownership of data & application + works closely with project manager to define critical success factors
User Management >> assumes ownership of project and resulting system (deliverables). Therefore, User management reviews & approves system deliverables.
Project manager >> day-to-day management + leadership
QA >>> reviews results within each phase and at the end of each phase to ensure compliance
System development management >> Technical support for hardware, software + ongoing operating support
System development project team or User project team >> completes assigned task
Security officer >> ensures controls provide protection
Infosec Engineer >> checking vulnerabilities
Privacy officer >> ensuring applicable privacy
Project Management Techniques
3 main elements >>>> deliverables, duration & budget
Total resource (TR) = Resource x duration (RxD)
Portfolio/Program Management
Program is group of projects
Project management office PMO >> controls projects, programs & portfolios
Types of programs
IS >> like ERP
Non IS >> like mergers & acquisition
Typical program roles:
Owner
Manager
Team
Project management office PMO >> Owner of project management ¦ Objective >> to improve project and program management and secure its success ¦ PMO can only focus on task & activates not the content of program/project
Portfolio objective >>> optimize projects as whole, not individually, prioritize and rank them
Project portfolio database >> mandatory for portfolio management ¦ has everything related to it like cost, roles, task, duration etc
Typical Reports:
1. Bar chart
2. profit vs risk matrix
3. Project portfolio progress graph
Project benefit realization>> ensure projects add value to business ¦ measurable business value ¦ Based on ROI >> return on investment ¦ benefit over cost
Project benefit realization>> ensure projects add value to business ¦ measurable business value
Project initiation: >> initiated by sponsor /project manager >> they gather information
Terms of reference/ Project charter >> objectives of project
PID >> project initiation document >> terms of reference/charter + information ¦ also called project request document ¦ this is then approved to start the project
Start meetings
One-on-One: Personalized discussions to align individual roles and expectations. Kick-off: Unified meeting to set goals, scope, and energize the team. Workshop: Collaborative session for detailed planning and risk mitigation. Mixed: Combines individual clarity with collective alignment.
Project objectives>> should be SMART
Approach for project objectives:
Object Breakdown Structure (OBS): Hierarchical (either graphically or table) representation of physical assets or system components in a project. Work Breakdown Structure (WBS): Hierarchical decomposition of project deliverables into manageable tasks. (baseline for cost & resource planning) Work Package: The smallest, manageable unit in the WBS, detailing scope, time, cost, and resources for specific tasks. ¦each WP should have distinct owner..
Project Planning >> cost + size
IS Development cost estimation
Analogous Estimation: Uses past project data for quick estimates. Parametric Estimation: Applies statistical models for accuracy. Bottom-Up Approach: Detailed cost calculation from individual tasks. Actual Cost: Real expenditures incurred during the project.
Software size estimation
SLOC >>> single parameter
FPA >> multiple parameters
FPA Parameters:
Inputs: Data provided to the system. Outputs: Data generated by the system. Queries: User interactions for retrieving information. Files: Logical internal data structures. Interfaces: Data exchanged with other systems.
Cost Budgets >> based on estimates of efforts
personnel hours
machines hours
other cost >> third party software licencing costs etc
Cost = (personnel hours x Rate) + (machines hours x rate)
Software cost estimation >> results of its size estimation
Scheduling and establishing time frame
Gantt Chart ¦ Visual timeline for scheduling tasks, showing start/end dates and task dependencies. ¦ progress tracking CPM (Critical Path Method) ¦ Determines the longest sequence of tasks (critical path) that must be completed on time to avoid delaying the project. PERT (Program Evaluation and Review Technique) ¦ Uses multiple time estimates (optimistic, pessimistic, most likely) to plan and evaluate task durations, with slack time for non-critical tasks and a critical path for key tasks. ¦ PERT is most effective when it comes to timeline ¦ Critical path is longest path on network, activities on critical path have zero slack time, we can say activities with zero slack time are on critical path ¦ when adding resources/premium it may change critical path, therefore critical path should be reevaluated to ensure "adding resources will reduce project duration". Time Box Management ¦ Sets a short & fixed period to complete a task, ensuring focus on prioritization and delivery within the set time frame. ¦ can be used in prototyping and RAD where time is short ¦ major advantage is prevents time delays ¦ System test and UAT are performed together
Example of slack time:
Imagine a project with three tasks: Task A (Duration: 5 days) Task B (Duration: 3 days, dependent on Task A) Task C (Duration: 4 days, dependent on Task A) Now, if Task A starts on day 1 and finishes on day 5, Task B can start on day 6 and finish on day 8, and Task C can start on day 6 and finish on day 10. However, if Task C finishes on day 10, but Task B could be delayed by 2 days without affecting the overall project timeline, Task B has 2 days of slack time. This means Task B can be delayed up to 2 days (until day 10) without impacting the project's final completion date.
Project execution >> start
Project controlling & monitoring >>> First step identify resources
management of scope changes >> change in WBS ¦ change in scope will change deadlines and budgets
Only stakeholders are allowed to submit change request to project manager through formal change request
When a change is required and supported by change control form then "checking in" is a process of moving an item to controlled environment. Then configuration manager will review the item in it.
All requests should be in project files
project manager evaluates impact of change (budget, time)
change advisory board approves changes on behalf of sponsor.
change is approved by sponsor
Management of resource usage >>> through EVA >> EVA is a project management technique that measures project performance by comparing planned progress with actual progress, integrating cost, schedule, and scope.
EVA metrics:
Budget to Date (BTD): The amount of money allocated for the project or activity up until the current point in time. (budget is always a projection not actual) Actual Spending to Date (ASTD): The actual amount of money that has been spent on the project or activity so far. Estimate to Complete (ETC): The estimated cost required to finish the project or activity from this point forward. Estimate at Completion (EAC): The total estimated cost of the project or activity at completion, which is the sum of the Actual Spending to Date (ASTD) and the Estimate to Complete (ETC).
Management of Risk: 2 main risks
1 Risk that impacts business benefits ¦ project sponsor is responsible to mitigate
2 Risk that impacts project ¦ project manager is responsible to mitigate this
Project closing >> handover to user/ system support staff
Key considerations for an IS auditor:
Final project notification >> when and who will send? project manager sends it
how will project manager address issues that remain open?
Two metrics to consider here:
TCO is the total cost of owning and operating an asset over its lifetime. ROI measures the return or profit from an investment relative to its cost.
TCO assesses the overall financial impact of ownership, ROI evaluates the financial returns gained from the investment.
IS auditor role in project development >> Controls Focus ¦ For this meet system development team and user project team member
identify existing control
identify weak controls and risk of their exposure
Track information on change management >> history, logon/logoff, deleted work, SOD, QA
Participate in post implementation review
Business Case & Feasibility study
Business Case >> information required to decide " whether a business should proceed"? ¦ ROI is most important to evaluate business case ¦ Business case is key for decision throughout the life of project. ¦ At any stage if business case is not valid "project sponsor or IT steering committee" decides to proceed or not. ¦ Well planned project has points to decide called stage gates or kill points.
If business case is valid then approve to move forward with project and start an analysis to define need and alternative for addressing this need. ¦ this analysis is feasibility study.
A feasibility study for a project includes 6 critical components: Project Scope – Defines the boundaries, objectives, and deliverables of the project. Current Analysis – Assesses the existing conditions or systems that the project will address. Requirements – Identifies the needs, specifications, and expectations from stakeholders. Approach – Outlines the method or strategy for executing the project. Evaluation – Assesses potential risks, costs, and benefits to determine if the project is viable. ¦ issue final report ¦ Report should have >> 1. total cost, 2. project start, end date 3. cost evaluation summary ROI etc Review – Regular assessments and feedback loops to ensure the project aligns with goals and feasibility.
Auditor role in business case >> how business defines business case¦ if business fails to meet ROI objectives then there are weaknesses in development and management of project
determine if solution can be achieved with existing resources
Determine reasonableness of chosen solution >> strengths and weakness analysis
Cost and benefits justifications are verifiable?
detailed requirement definition in place?
reasonable numbers of vendors proposed the project?
UAT specifications?
determine if application is critical and falls in embedded audit routine?
Types of developed business applications systems
organization-centric >> objective >>> to collect, store, archive and share information with business users. ¦ use detailed SDLC
end-user centric >> to provide different views of data ¦ objective to provide DSS or GIS. A DSS (Decision Support System) helps in decision-making by analysing data, while a GIS (Geographic Information System) manages and analyses spatial data for decision-making.
SDLC Models
Waterfall Model: Linear and Sequential: Each phase must be completed before the next begins (e.g., Requirements, Design, Implementation, Testing, Deployment, Maintenance). Best for: Well-defined projects with clear requirements and no expected changes. V-Model (Verification and Validation): Extension of Waterfall: Emphasizes validation and verification steps alongside development stages. Parallel Phases: Each development phase has a corresponding testing phase (e.g., Requirements -> Unit Testing, Design -> Integration Testing). Best for: Projects with clear, fixed requirements, similar to Waterfall but with more focus on testing. Iterative Model: Cyclic and Incremental: The project is developed in small, manageable iterations (or sprints), each producing a working part of the software. Best for: Projects with evolving requirements or when feedback is needed early in the development process.
SDLC phases
Feasibility Study: Assess the project's technical, financial, and operational viability. Requirements Definition: Gather and document detailed functional and non-functional requirements. (The system must allow users to log in using a username and password (functional) and respond to login requests within 2 seconds (non-functional)). Software Selection & Acquisition: Select and purchase a suitable external system or solution. a. Purchase the system: Buy a third-party software solution. b. Design In-House: Create a custom design for an internal system. Configuration of Purchased System: Adapt and configure the purchased system to fit organizational needs. a. Configure the purchased system: Modify the purchased software to align with requirements. b. In-House Development: Build a custom system based on internal design. ¦ programming ¦ various levels of test are done at this phase ¦ general >> all units, system test and UAT ¦ Final Test & Implementation: Conduct testing and deploy the system into production. Post-Implementation: to ensure system is operating as designed ¦Provide ongoing support, maintenance, and monitoring of the system. ¦ ROI
Details feasibility study
1. Feasibility Study ¦ defines time frame, risk-based solution selection, compatibility with IT system ¦ Impact assessment >> potential future effects of a development project on current projects & resources. ¦ Results of feasibility study determine organizational impact > a comparison report of cost, benefits and risk. 2. Requirements Definition ¦ specification of system ¦ Active involvement of user/user groups 3. Software Selection & Acquisition ¦ in standard SDLC Acquisition is not a phase in standard SDLC but if its is decided to purchase the system then it should be done after requirements definition. a. Purchase the system ¦ Prepare RFP ¦ User MUST be actively involved in package evaluation and selection process. ¦ Contract review & approve from legal council is most important in acquisition. b. Design In-House ¦ Programming, blueprints of system, flow charts, processing step, computation rules, data file database systems ¦Establish baseline of system based on requirements ¦ Most importantly >> Test plans: unit (program), subsystem (module), integration (system), interface (with other systems), loading initializing, stress, security, backup & recovery. ¦Data conversion plans, Risk assessment of data flows ¦ Involvement of user is limited but user approval lies here. ¦ implementation plans are developed in this phase. 4. Configuration of Purchased System a. Configure the purchased system ¦ best do configurations than changing program code. b. In-House Development 5. Final Test & Implementation Before UAT full system test ¦Final test = QAT + UAT ¦ Final UAT & user sign-off ¦ System may go for certification or accreditation (before implementation) to assess if this is effective to mitigate risk at appropriate level. ¦ After Successful full-system test, system is ready to migrate and date for migration is determined. ¦ In case of acquired project implementation should be done by user management with the help of IS management to avoid vendor unauthorized changes. ¦ A security test such as pentest is also performed at this phase. 6. Post-Implementation review >> to verify system has been designed and developed properly and proper controls are built into it.
Dealing with deviations
In case there is deviation (but this deviation should be based on risk identification and compensating controls) from predefined procedures (like system acquired from internet information not from RFQs) IS auditor should first ensure procedure followed is consistent with business objective and approved by appropriate authorities.
Remember : These deviations should be based on risk identification and compensating controls (for example deviation in configurations must be assessed on risk identification and compensating controls basis.
how to identify deviation from project plan? Project performance is baseline.
How to evaluate quality of new software developed and implemented? First report of mean time between failures. ¦ if rapid fails it means >> poorly developed.
Auditor role in SDLC >> Analyse risk in each phase & validate cost effective controls
Additional Considerations in software design phase
Risk associated with software development
Strategic Risk: Misalignment with company goals, wasting resources. 2. Business Risk / Benefit Risk: Project may fail to deliver expected business value or ROI. 3. Project Risk / Delivery Risk: Within Project: Scope creep, poor planning, or resource issues causing delays. With Supplier: Suppliers failing to deliver on time or meeting quality standards. With External Environment: Economic or regulatory changes affecting project success. With Technology Chosen: Chosen technology becoming obsolete or incompatible.
Use of Structured Techniques in Software design
Entity-Relationship Diagram (ERD): Visual representation of data, helping ensure good system design. Software Baselining / design freeze : Optimum point for baseline to occur >> cutoff point in design ¦ requirements are considered each in detail in terms of cost and time. ¦ if baselines not followed can result in several risk and scope screep is one of them ¦RISK scope creep >> is the uncontrolled addition of new features or changes to a project after it has started, leading to delays and cost overruns User Involvement (Limited but Approval): Users approve key stages but are not involved in every phase.
Auditor role in project design >> primary focus on adequate controls ¦ whether continuous audit functions built into system? Particularly, in ecommerce and paperless environments. + evaluation of design process + Perform risk assessment
Additional Considerations in software development phase
Online programming facilities provided by Integrated Development Environments (IDEs): Programming Languages: Support for multiple languages with syntax highlighting and code completion. Program Debugging: Tools to identify and fix errors, including: Logic Path Monitors: Trace the flow of program execution. Memory Dumps: Examine memory state during execution. Output Analysers: Analyse program output to identify inconsistencies or errors.
Software development methods: Prototyping/Evolutionary Development (also called heuristic or evolutionary development): Quickly deliver a prototype means "Model" to gather early user feedback. ¦ Initial focus is placed on "Reports & Screens" ¦ Significant time and cost saving. ¦ Risk: poor controls and complicated change control because modification in requirements and design are so rapid. Rapid Application Development (RAD): Develop important system quickly (first). ¦ Reduces development cost and maintains quality ¦ RAD require > good expertise + fast decision making ¦RAD supports analysis, design, development and implementation but doesn't support planning. ¦ Core of RAD is prototyping. a. Concept Definition Stage: Identify scope and objectives. b. Functional Design Stage: Define system functionality and user interfaces. c. Development Stage: Build the system. d. Deployment Stage: Implement and deliver the system. Agile Development: assumes that all requirements can not be expressed at once ¦ Agile is incremental not sequential, therefore, planning at each phase (called sprint in SCRUM approach). ¦ time-boxed small projects ¦ Reliance on tactic knowledge >> knowledge that is in the head of people ¦ pair-wise programming (two person code same part of system, knowledge sharing¦ Only plans next iteration not all at once. ¦ avoid repeated tasks. ¦ one of most important features of agile is post-iteration reviews that identify lessons learned after each iteration. ¦ team learning (refining project) is key in agile therefore, a disciplined team can deliver releasable software in 4-8 weeks.
Object-Oriented System Development: Entity: Represents a distinct object or concept within the system (e.g., a customer, product, or order). It is modelled as an object in OOSD. Data: Refers to the attributes of an entity. These are the properties or characteristics that describe the entity (e.g., a customer might have data like name, age, and address). Method: Refers to the behaviour of an entity. These are the functions or operations that can be performed on the data or by the entity (e.g., a method could be "update address" for a customer object) ¦OOSD polymorphism (means many forms) lets different objects use the same method name but behave differently ¦ OOSD >> reuseable code ¦ OOSD >> Uses traditional waterfall approach ¦ Applications >> web apps, e-business apps.
Component-Based Development: like assembling >> it assembles packages of executable software, pieces of programs called objects. ¦ primary benefit >> ability to buy "proven & tested" software from third-party. ¦ reduces time, focus on business needs ¦ modules are build instead of units. ¦ Major advantage of component- based Development >> supports multiple development environments ¦ 4 important components to understand: a. In-Process Client Component: Runs within the client application process. b. Stand-Alone Component: Independent module used by applications. c. Stand-Alone Server Component: Provides services to client apps over a network. d. In-Process Server Component: Runs within the server application process. Web Application Development: Focuses on building browser-based solutions.
Software Reengineering >> involves revisiting and improving existing software systems to enhance functionality, performance, or maintainability. 1. Business Process Reengineering (BPR): - Focuses on radically redesigning core business processes to achieve dramatic improvements in productivity, efficiency, and quality. - Involves analysing and redesigning workflows and processes within the organization, often leveraging technology to automate or optimize these processes. 2. Service-Oriented Software Reengineering (leveraging RACI): - Involves refactoring existing software systems to adopt a service-oriented architecture (SOA), where functionalities are encapsulated into services that can be reused across applications. ¦ Refactoring for SOA means breaking down a single large application into smaller, independent services, like creating a standalone service for user authentication. - RACI (Responsible, Accountable, Consulted, Informed): A framework used to clarify roles and responsibilities in processes, ensuring clear accountability and efficient communication during the reengineering process, especially when transitioning to a service-oriented model. It helps define who is responsible for reengineering tasks and ensures alignment between different teams.
Reverse Engineering >>> to see how a software works Process: - Decompiling: Converting compiled code into human-readable source code to analyse or understand the software's behaviour. - Blackbox Testing: Testing the software without knowledge of its internal workings, focusing on input/output behaviour without accessing the source code. Risk >> Software Licensing: Reverse engineering may violate software licenses, as many licenses explicitly forbid decompiling or other reverse engineering activities.
DevOps & Develops: Integrates development, operations, and security for streamlined delivery. Benchmarking Process: Compares performance metrics against best practices or standards.
Business process reengineering and process change >> process is changed and outcome is measured against a goal.
Measurement: Effective ( goal achievement) , Efficient (minimum effort)
Can be architected through ERP also called PER >> packaged enable reengineering
First step >> define areas to be reviews/ improved
existing process must be documented preferably in flow chart so it can be compared..
Risk >> controls may be reengineered
Role of IS auditor:
check controls
BPR minimize efforts
lesson learned are documented
System Development Tools and Aids CASE: Tools that aid in software development and maintenance. - Upper CASE: Tools for planning and design. - Middle CASE: Tools for implementation (coding, testing). - Lower CASE: Tools for maintenance and updates. Code Generators: Automatically create code from specifications. 4GLs: High-level programming languages for faster, simpler development (e.g., SQL, MATLAB).
hardware acquisition
Phase 1: Vendor Selection Review of existing architecture >> Architecture Workshop 1 Analysis and design Draft functional requirements >> Architecture Workshop 2 Functional requirements (presentation and discussion) Final functional requirements >> Architecture Workshop 3 Proof of concept (delivery of prototype)
Phase 2: Planning and Implementation of Infrastructure Requirement analysis Procurement phase 1. Vendor evaluation 2. Vendor long list 3. Vendor shortlist 4. Select vendor 5. Define partnership Delivery time Installation plan Installation test plan
Hardware/software acquisition vendor evaluation criteria
Project schedule: Timeline for completing the project or delivering the solution, including milestones and deadlines. Turnaround time: Time taken by the system to complete a specific task or action from start to finish. ¦ specific task¦ Response time: Time it takes for the system to react to an input or request. System reaction time: The speed with which a system responds to a command or input. Throughput time: Time taken to process a set of operations or tasks from start to finish. ¦ set of tasks¦ Workload: The volume of tasks or processes a system is handling at a given time. Compatibility: How well the system integrates with other systems or software without conflicts. Capacity: The maximum amount of work or data a system can handle or store.
Important Request for proposal contents
sociability & interoperability >> ability to interact with other systems
customer reference
Vendor financial stability
source code availability >> escrow agreement
acceptance testing of product before purchase
Application controls ¦ Application Controls can be bypassed through collusion attack ==> its an active attack, employees collaborate to bypass ¦ such breaches are difficult to identify.
Input controls
Input authorization >> verifies all transactions are authorized >> unique passwords, terminal IDs, online access controls etc
Accountability controls in input data:
SOD
activity reports
violation reports
Batch controls and balancing ¦ Batch >> refers to a group or set of items processed together in a single operation
Controls:
total momentary amount
total items
total documents
hash totals
Processing procedures & controls
Data validation edits & controls
Validity check >> correctly entered as per predefined criteria like Gender : Male / Female no other value can be entered.
Existence check >> correctly entered as per predefined criteria like code in code field
Key Verification >> repeated by separate individual
Check digit >> detect transposition and transcription errors
Output controls >> balancing, reconciliation etc
System readiness and implementation tests
Alpha & beta test >> two phases before software considered finished
1. Alpha testing >> within enterprise who are developing software for example system testing.
2. Beta Testing >> its form of UAT (since user are involved but outside the organization) ¦ limited number of external users ¦ real-world exposure / live environment ¦ sending to independent test sites or for free to interested users.
white box >>> program logic, procedural accuracy ¦ Applicable to unit and integration testing ¦ for large systems its expensive so should be done on selected basis.
Black box testing >> integrity based ¦ to check functional operating effectiveness ¦ applicable to integration(interface) and UAT.
Function/Validation testing >> to verify built functions/system against detail requirements..
Parallel Testing >> to determine does new system performs same way the original? ¦ data in entered in both systems (new and old) and results are compared.
Sociability test >> to check ability of new system to work in target environment without causing adverse effect on existing system..
Software testing approaches
Bottom-up >> begins with atomic units, like program -> module -> system ¦ no need for stub/drivers (dummies) ¦ testing before program complete and early error detection in critical modules
Top down >> test of functions & processes first ¦ user feedback is grabbed early.
Data integrity Testing
Relational Integrity Test: Ensures data accuracy and consistency within a table (e.g., enforcing valid values in columns). ¦ achieved by input constraints and/or data characteristics Referential Integrity Test: Ensures consistency between related tables, verifying that foreign keys correctly reference primary keys. ¦ achieved by ensuring all reference to primary key from foreign key exist in their original table.
Data integrity in online processing system
Atomicity: All-or-nothing execution. Consistency: Transitions the system from one valid state to another. Isolation: Transactions do not interfere with each other. Durability: Committed transactions are permanent, even after a crash.
Testing Application systems
Snapshot: A snapshot verifies program logic by capturing the program's state at a specific point, comparing it with expected outcomes to ensure the correct logic path is followed.
Mapping >> identifies specific program logic that has not been tested + analyses programs during execution
Tracing & Tagging > trail of instructions executed.
Tracing: Records the sequence of executed statements. Tagging: Marks specific parts or variables to track their behaviour.
Test Data/Deck: A collection of input data used to test and validate a program's functionality. ¦ can be copy of actual data / dummy
Integrated testing facility >> Test files + live transactions running simultaneously
Implementation approaches >> parallel, abrupt, phased
Certification/Accreditation ¦ in nonproduction environment to place approved system in production.
Certification: A detailed assessment of how controls in an IS meet security requirements. Its primary goal is to determine the extent of control implementation. Accreditation: Defined as an official management decision by a senior authority. It explicitly accepts the risks to the organization's operations, assets, or individuals. Acts as a form of quality control (QC). Principles: Focus on responsibility and accountability, ensuring senior officials accept full accountability for system security.
Certification is about evaluation and validation. Accreditation is about acceptance and accountability. ¦ Officials accepting accountability in case of breach.
Post implementation review >>> project development team + end user ¦ after several weeks / months
Auditor role in post implementation review >> Independent ¦ if IS auditor patriated in development (whether it is consulting) should not perform this review.
All audit work during development should be thoroughly documented in audit work papers to support audit findings and recommendations.
Common System test
Load Testing: Measures system performance under expected normal and peak loads. (e.g. users limit 100, normally working users 40 and peak working users 90)
Volume Testing: Tests system behaviour with large data volumes (e.g., database size).
Stress Testing: Assesses system limits under extreme or abnormal conditions (abnormal number of users). (users limit 100, normally working users 40 and peak working users 90, abnormal users 150)
regression test >> new system doesn't create a new error
Socialability test > system can run in its target environment ¦ works with other components
parallel testing > comparison of two applications (new and old)
System Testing > basically series of tests, ensures system correctly interacts with other components ¦ Focuses on "functional working/ functional requirement".
Remember: Postproject review (lessons learned) is different from post-implementation review (system working as designed).
Post project review focuses on project-related issues (overall). Project team has something to learn from every project. ¦ Therefore, lessons learned are core of this key.
Other points
when it comes to check transferring of transactions then Automatic numerical sequencing (not synchronization date/time ) is the only option that accounts for completeness of transactions because any missing transactions are identified by a gap. ¦ because synchronization can inform about time/date of transaction not which have been missed.
Escalation means raising an issue to a higher authority or level of management when it cannot be resolved at the current level. For example if any error is reoccurring and not correct at current level then Auditor should escalate this issue to higher management.
Data warehouse : copy of transaction data. Metadata : table of contents + stored information
when migrating data between two systems (old to new) there should be a correlation of there semantic characteristics which means both systems interpret data same way.
Basis of validating of credit card transactions begins with "verifying card number + pin".
Automated release management software > ensure tested code is code that is moved in production ¦ which means unauthorized/unrest code can not be moved in production ¦ it does not require manual intervention.
Ad hoc software deployments >> software changes without proper planning or documentation >> and this is not good practice.
CI/CD deployment >> Main benefit / Main Goal >> speed for creation and delivery of software ¦ "Standard Maintenance changes" is a must document, this is documentation of all changes.
Pointer manipulation >> coding issue
Automated System Balancing >> BEST way to ensure that no transaction are lost
Production data can be used for testing if senior IS + business management approve the use.
when is comes to quality of programming activities related to future maintenance capabilities then follow program coding standards.
When QAT and UAT are combined there is a risk that users may apply pressure to accept a program that does not meets QA standards (improper/poor program acceptance).
How to assure that project can meet its target date? Directly observe/compare/extrapolate "completed work packages (WP) and current resources".