## ISO 27001 Compliance Checklist
ISO 27001 Compliance Checklist
For Company [XYZ]
ISO 27001 Compliance Requirments | Tasks | Status | Progress % | Priority | Notes (If any)
1. Establish Your ISMS Plan | Outline how your information security management system (ISMS) will be set up and certified. | Not Started | 0 | High
| Use the PDCA cycle to guide improvements and close security gaps. | In Progress | 50 | Medium
| Budget realistically based on your company’s size. | Completed | 100 | Low
Keep track of progress with simple project planning methods.
Decide early on what areas of the business will be included in the certification.
2. Define the Scope of Your ISMS | Identify which parts of the business will be included under the ISMS.
Exclude areas that don’t fall within the security program’s boundaries.
Apply extra safeguards to any process that exchanges information across internal or external boundaries.
Make sure stakeholders understand what is and isn’t covered.
3. Form Your ISMS Team | Appoint skilled staff to design and implement required security controls.
Set up a governance group with management involvement.
Include senior leadership to oversee strategy and resource allocation.
For larger organizations, assign a project manager to keep progress on track.
Ensure everyone understands the project scope, earlier planning steps, and their specific responsibilities.
4. Document Your Information Assets | List everything that stores, processes, or provides access to information.
Capture both information and people-related assets.
Include physical assets like laptops, servers, and office locations.
Don’t forget intangible assets such as intellectual property, brand value, and reputation.
Assign each asset a classification level and designate an owner to ensure it’s properly managed and protected.
Review the inventory with your team to confirm accuracy and alignment.
5. Carry Out a Risk Assessment | Define a risk management framework to keep the process consistent.
Identify situations where information, systems, or services may be exposed.
Estimate how likely each scenario is to happen.
Assess the potential effect on confidentiality, integrity, and availability.
Prioritize risks based on their impact on business objectives.
6. Create a Risk Register | Document the risks uncovered during your assessment.
Provide a brief description of each risk.
Note its likelihood and potential impact.
Rank the risks so the organization can focus on the most serious ones first.
7. Prepare a Risk Treatment Plan | Decide how each identified risk will be addressed.
Assign responsibility for both the risk and its mitigation actions.
Set deadlines for completing treatment tasks.
Put the plan into action and monitor progress regularly.
8. Finalize the Statement of Applicability (SoA) | Review the 93 Annex A controls.
Choose the controls that address the risks found in your assessment.
Document all controls in the SoA, explaining why each one is included or excluded from your ISMS.
9. Implement ISMS Policies and Controls | Assign responsibility for each control and set clear progress goals.
Establish a process to monitor and measure implementation.
Create a framework to maintain and continually improve the ISMS.
10. Build Training and Awareness Programs | Set clear expectations for staff on their role in maintaining the ISMS.
Provide training on common security threats and appropriate responses.
Define consequences for non-compliance with security requirements.
Include security training in new employee onboarding.
Offer ongoing sessions to keep employees updated on new policies and procedures.
11. Hold Regular Management Reviews | Schedule reviews at least annually, or quarterly for larger or fast-changing organizations.
Confirm that the ISMS and its objectives remain effective.
Keep senior management updated on results.
Address risks and gaps quickly through the review process.
12. Conduct an Internal Audit | Review all Annex A controls included in your Statement of Applicability to confirm they are in place.
Use internal staff who were not involved in developing the ISMS, or bring in an independent auditor.
Share audit findings, including any nonconformities, with the ISMS team and senior management.
Resolve issues identified during the audit before moving to external certification.
13. Complete the External Audit | Choose an accredited ISO 27001 auditor.
Undergo Stage 1 Audit to review documentation and confirm readiness for the next step.
Proceed to Stage 2 Audit, where the auditor tests your ISMS to verify design, implementation, and ongoing effectiveness of controls.
14. Fix Nonconformities | Resolve any issues highlighted during the audit.
Confirm full alignment with ISO 27001 requirements.
Ensure documented processes are being followed in practice.
Check that third-party contractual obligations are being met.
Provide proof of corrective actions to the auditor and obtain final approval.
15. Plan for Ongoing Audits | Schedule a full ISO 27001 recertification audit every three years.
Prepare for surveillance audits in years two and three of the certification cycle.
Keep your ISMS audit-ready at all times by maintaining documentation and continual improvement.

## How to use
How to Use This Checklist Table
ISO 27001 Compliance Requirements → List of major tasks.
Tasks → Break down what needs to be done for that requirement.
Status → Choose Not Started / In Progress / Completed.
Progress % → Automatically updates based on status
Priority → Mark tasks as High / Medium / Low.
Notes (If any) → Add extra details, reminders, or explanations (e.g., “Need manager approval”).